## Group 6 Details
Members of Group 6:
1 | Nishant Bharadwaj | 404/2021
2 | Aman Sareen | 411/2021
3 | Rahul Bhutra | 418/2021
4 | Daksh Kapoor | 424/2021
5 | Prateek Rai | 434/2021

## Project Charter
PROJECT CHARTER
Project Name/Number | Anurag weds Priyanka |  |  | Customer: | Mr. & Mrs. Sareen | Contact Person: | Mr. Aman Sareen Email: aman@pqr.com Contact No.: 9012102600
Project Type: | Service
Prepared by: | Group 6 |  |  | Approved by: | Mr. Rahul Bhutra | Date: | 01.03.2022
Project Information
Project Manager | Mr. Dakh Kapoor (Email: daksh@xyz.com, M: 7276920704)
Project Manager Responsibility | Ensuring all deliverables reach at their prescribed time and is as per approved requirements of Mr and Mrs. Sareen. Ensure all laboureres at the destination are working at Venue. Regulate all the expenses and maintain the prescribed budget while ensuring hospitality to all guests. Recruiting employees to execute stipulated tasks and Negotiate with the Venue Owners, Caterers for adequate quality, quantity of all resources.
Authority Levels & Approval Matrix | TASKS | Saurabh | Faraz | Aditi | Lavisha | Shilpi
| Create guest list | S | I | - | - | R
| Print the invitations | - | C | S | I | R
| Mail the invitations | - | - | C | S | R
| Wait for RSVPs | S | - | S | - | R
| Finalize the number of rooms required | R | S | I | A | -
| Select the hotel | R | S | C | - | -
| Book the rooms | R | S | - | C | S
| Find the caterer | C | - | R | S | -
| Finalize the menu | A | C | R | S | -
| Finalize the number of serves | A | - | R | S | A
| Selecting the Décor Vendor | - | S | - | R | C
| Selecting DJ, Music Band | R | C | A | - | -
| Cater wedding | C | S | R | S | -
| Shop for the dress | S | A | - | R | S
| Booking Tickets | S | - | A | R | C
| Buy gift for Guests | - | - | C | A | R
| Choose halls and lawns | S | A | - | R | C
| Tailoring and fitting | S | C | A | R | -
| Makeup | S | - | A | R | C
| Finalize the Iist of events | A | R | - | A | S
| Buying all the ritual materials | - | - | R | A | C
booking for ghori and doli
| Identify the service provider | C | R | A | S | S
| Pay Advance to book | A | R | A | - | S
RASIC-Responsible, Approving, Supporting, Inform, Consulting
Project Stake Holders | Aman(Groom), Priyanka(Bride), Venue Owner, Mr. and Mrs. Sareen & Mr. and Mrs. Arora along with all their relatives and contributors.
Core Team Members | Analyst, Project Manager and his Team, Vemnue Owner, Band Owner, Caterrers
Other Key Resource Requirement | Dresser, Flowerist, Food, Transportation, Ghori, Venue decoration, Hotel requirement
Supporting Elements
Completion Criteria | The work executed by Project Manager has to be in context to the budget estimated within the defined scope of work and as must the the desired satisfaction of the two families
Milestones/ Deliverables | The project's essential milestones being Confirmation of booking of flight tickets and hotel reservations, booking of music, band and DJ, Wedding attire for bide and groom, Arrangement of Catering, Theme and Decorations, Arrangement of Photographers and Makeup artists. The other deliverables being the food to be seved, decorations of the venue, flowers required, Jwellery and Other gifts incorporated.
Project Constraints | Constraints being the budget, the unavailability of desired venue, delay in alterations, delay in delivery of deliverables, any additional change of plan or addition to the checklist
Assumptions | We will be able to find vendors who can accommodate our budget and are available on the date of our wedding All important family members and friends will be able to attend Money provided by parents for the budget will be available when needed Flights and hotel are available on the specified dates as well as the ceremonies.
Project Risks | Risk on Schedule change at any point of time. Risk of excess cost incurred. Quality issues of the deliverables, serivces offerred by any of the vendor. The unexpected risks involed. Invitation Risks i.e not the estimated number of people appearning on invite and people apart from guest list entering the venue, guests not sending RSVPs/confirmation, postal delays or address missing on postages. Accomodation risks which involves the cleanliness, shortage of rooms, checkin-checkout time issues, hospitality. Fodd quality and unavailability/shortage of food, food being served cold, lack of tissues, untidy area around food, late preprations, wrong stage arrangements, music malfunctioning, the late arrival of mangers, shortage of power supply.
Brief Description of:
- Spending Limits | 80-90% of total estimate
- Project Priorities | all arragements and confirmations shall be done 15-30 days prior to the wedding
Project Scope Statement
Project Goals | To execute a successful, hinderances free wedding for hosts as well at invitees
Project Deliverables | The Makeup artist, Music, Flowers, Gifts, Jwellery, Food, Decorations for stage, venue, entarance, Ghori, Power Backups, Hospitality staff.
Budget | Rs. 90,00,000 (Rupees Ninety Lacs)
Project Exclusions | After wedding Cleanup of venue, any mishandling of rented comodity, break/stole of crockery or any equipment rented

## CheckList and Work Packages
Main Deliverable
Date of Wedding
Budget Estimation
Contribution
Wedding Style
Photographer
DJ
Wedding Dresses
Barat - Ghodi etc
Honeymoon Destination
Logistics
Venue (Decoration)
Caterer - F&B
Invitations
Events | Mehandi | Cocktail
Accomodations
Jwellery
Groom / Bride Package
SPA
Guests
WORK PACKAGES
PHOTOGRAPHY & FILMING | APPAREL | STATIONERY
Pre-Wedding Shoot | Alterations | Address labels
Roka | Bridal headpiece/veil | Cards - Ceremony
Ring Ceremony | Bridal shoes | Cards - Map/direction
Mehandi | Bridal slippers | Cards - Reply
Bachelor's Party | Bridal accessories | Cards - Save the date
Haldi | Gown | Invitations - Bachelor party
Wedding ceremony | Groom's tuxedo | Postage
Reception | Groom's shoes | Wedding programs
Groom's accessories
FLOWERS | RECEPTION | GIFTS & FAVORS
Altarpiece | Baker | Favors
Brides bouquet | Balloons | Gift for fiancee
Reception centerpieces | Bar tender
Throw away bouquet | Cake | MISCELLANEOUS
| Cake decorations | Consultant/coordinator
BACHELOR'S PARTY | Cake knife | Hairdresser
Bartender | Caterer | Hotel for guests
Caterer | Chairs | Make-up
Decorations (with Lights) | Decorations - Other | Manicure/pedicure
Dishes | Decorations - Table | Manicure/pedicure for attendants
Food | Dishes | Marriage license
Liquor | Entertainment | Wedding planner/organizer
Sound system | Food
Tables/chairs | Gratuities
Liquor
Musician
Napkins
Parking / Valet
Transportation
CEREMONY
Chair/pew rental
Guest book/pen
Location fee
Ring bearer pillow
Transportation
RINGS
Engagement ring
Engraving
Wedding bands
HONEYMOON
Accommodations
Air fare
Entertainment
Rental car / Transportation
LOGISTICS
Arranging Transpotations
Guests from Other Cities
Arranging Bus/Transport for localites
Arranging Refreshment
Finalizing Caterer/Vendor
Finalizing Menu from the Vendor